## Basic Project with Gantt _ Depe
At Risk | Task Name | Start Date | End Date | Assigned To | Duration | % Complete | Predecessors | Comments
- | Watch how-to video on this template (4:16)
- | Click to learn how to use this template
| Documentation | 2016-03-29 | 2016-05-10 |  | 31d | 100%
| Product Backlog | 2016-03-29 | 2016-05-10 | Dravid | 31d | 100%
| Code Documentation | 2016-03-29 | 2016-05-10 | Dravid | 31d | 100%
| State Diagram | 2016-04-05 | 2016-04-07 | Richard | 3d | 100%
| Use Case Diagram | 2016-04-05 | 2016-04-07 | Richard | 3d | 100%
| Class Diagram | 2016-04-05 | 2016-04-07 | Richard | 3d | 100%
| Gantt Chart | 2016-05-01 | 2016-05-10 | Dravid | 8d | 100%
| Teammate Assessment | 2016-05-10 | 2016-05-10 | All | 1d | 100%
| Self-Assessment | 2016-05-10 | 2016-05-10 | All | 1d | 100%
| Code Tasks | 2016-03-29 | 2016-05-10 |  | 31d | 84%
| Basic Templates | 2016-03-29 | 2016-04-07 | Francinaldo | 8d | 100%
| Add Function to Search Button | 2016-04-07 | 2016-04-07 | Jinuk | 1d | 100%
| Add Template Movie Pages | 2016-04-07 | 2016-04-07 | Jinuk | 1d | 100%
| Add Server-side functionality to Project | 2016-04-06 | 2016-04-08 | Dravid | 3d | 100%
| API Call for search | 2016-04-13 | 2016-04-13 | Jinuk | 1d | 100%
| Code Cleanup | 2016-04-14 | 2016-04-14 | Jinuk | 1d | 100%
| Add Movie Info Page | 2016-04-15 | 2016-04-15 | Jinuk | 1d | 100%
| Stich API to server | 2016-04-16 | 2016-04-16 | Jinuk | 1d | 100%
| Code Cleanup | 2016-04-17 | 2016-04-18 | Jinuk | 2d | 100%
| Enable purchase API Call | 2016-04-19 | 2016-04-19 | Jinuk | 1d | 100%
| Add Movie Overview on Landing Page | 2016-04-20 | 2016-04-20 | Jinuk | 1d | 100%
| Fix Search Button | 2016-04-21 | 2016-04-21 | Jinuk | 1d | 100%
| Open More Information in New Tab | 2016-04-22 | 2016-04-22 | Jinuk | 1d | 100%
| Enable Show search | 2016-04-23 | 2016-04-23 | Jinuk | 1d | 100%
| Change Poster Image Default | 2016-04-24 | 2016-04-24 | Jinuk | 1d | 100%
| Display most popular movies and shows | 2016-04-25 | 2016-04-25 | Jinuk | 1d | 100%
| Create show info link | 2016-04-26 | 2016-04-26 | Jinuk | 1d | 100%
| Reformat web Page | 2016-04-27 | 2016-04-27 | Jinuk | 1d | 100%
| User Login | 2016-04-16 | 2016-05-10 | Dravid,Francinaldo | 18d | 50%
| Moving to Laravel framework | 2016-04-28 | 2016-05-10 | Francinaldo | 9d | 100%
| Move to Amazon host | 2016-05-06 | 2016-05-06 | Francinaldo | 1d | 100%
| Final | 2016-05-06 | 2016-05-10 |  | 3d | 100%
| Test Suite | 2016-05-06 | 2016-05-10 | Richard | 3d | 100%
| Bug List | 2016-05-10 | 2016-05-10 | Dravid | 1d | 100%
| User Manual | 2016-05-10 | 2016-05-10 | Dravid | 0 | 100%
| Deployment Plan | 2016-05-09 | 2016-05-09 | Dravid | 1d | 100%
| Maintenance Plan | 2016-05-10 | 2016-05-10 | Dravid | 1d | 100%
| Exit Interview | 2016-05-10 | 2016-05-10 | All | 1d | 100%

## Discussions
Row 6 | Discussion Title | Sub-task 2 | Jenny Gruening | 06/27/13 9:02 AM
| Comments | You can add discussions, notes, or emails to discussions. | Jenny Gruening | 06/27/13 9:02 AM